Fall 2015 Program Review Timeline

|  |  |  |  |
| --- | --- | --- | --- |
| Date | Task | Group Responsible | Output |
| ASAP | College goals & District Goals post to moodle | VPI/VPI Asst. | Incorporated into the Program review – goals alignment form. |
| 10/15 | Discipline/Program complete initial Program Review | Leads | Initial Program Reviews to Chairs |
| 10/15-10/30 | Post peer evaluation form (use validation form as template) | VPI/VPI Asst. | Post on moodle for use by chairs 11/2-11/6 |
| Create website for new Program Review Cycle | VPI/Webmaster | Ready for unvetted PR to post by 11/2 |
| 10/30 | Department Program Reviews to VP, VPI Asst. & Deans | Chairs | Completed unvetted PR |
| Post unvalidated program review plans on moodle | VPI Asst. | For internal review |
| 11/2-11/6 | Chairs peer review of plans | Chairs | Understanding of each other’s area, ID common needs |
| Dean review of all plans | Deans | Summary of themes across plans |
| VPI office to compile resource requests | VPI/VPI Asst. | Compilation of resource requests prepared for shared governance and Admin to use |
| 11/9-11/12 | Integrate peer feedback into Final Program Review | Chair | Unvalidated Final PRs posted on the website 11/12 |
| Dean’s complete a summary for all areas | Deans | Dean’s Summary posted on moodle 11/12 |
|  |  |  |
| 11/13 | Report out to Chairs Dean’s summary and unvalidated final PRs | Chairs/Deans | Common message/package of dean’s and program review to go out to the campus community for review. |
| 11/16 | Roundtable review summary from chairs and deans |  | Dean’s will present summaries |
| 11/18 | Senate Review |  |  |
| 11/19 | Validation | Ed/PIE Validation |  |
| 12/3 | Summary from Validation | Ed/PIE Validation |  |
| 12/7 | Roundtable review summary from Ed/PIE along with Dean’s summary |  |  |
|  |  |  |  |