## Sheet1
BCC ISER Steering Committee and Writing Team Timeline and Activity Schedule 2019-2020
Steering Committee meetings | Steering Committee focus | Writing Team Timeline or meetings | Writing Team activities and focus | Evidence Tream
|  | 2019-10-04 | * Confirm Faculty ALO * Confirm Faculty or Classified Co-leads per the standard | * Team set up * Review ACCJC format * Identify depository * Ask participatory governance to start organizing agendas and minutes from 3 years ago.
2019-10-07 | *Introduction of the Steering Team *Writing team set up process * Review of the writing process (Draft Development) * Review Guide to Institutional Self-Evaluation, Improvement, and Peer Review (Possible Source of Evidence and Review Criteria) * Review Timeline
|  | 2019-10-17 | * Writing members of each Standard to be confirmed by the Co-Chairs
2019-10-21 | * Share writing team members (co-leads) * Review overall process: format for responses to the questions. * Begin bullet points of outline per question. * Evidence collecion begins per Standard |  |  | * Coordination with the writing team
|  | 10/21 - 11/4 (2 weeks) | * Each writing team designate members to wrok on questions within the standard * Begin producing outlines
2019-11-04 | * Check on progress on the outlines & evidence |  |  | * Coordination with the writing team
|  | 11/5 - 11/18 (2 weeks) | * Bullet points productin & evidence collection continues
2019-11-18 | * Chek on progress o the outlines & evidence |  |  | * Coordination with the writing team
|  | 11/19 - 12/1 (2 weeks) | * Be ready to complete bullet points/outlines by 12/2/19
2019-12-02 | *Outline completed, be ready to write narrative *Discuss Narrative writing based on the bullet points, set timeline for writing process for spring 2020 *Member assignments for writing narrative completed. |  |  | * Coordination with the writing team
(12/16/2019) | * Additional time to regroup as necessary to be ready for writing
(1/6/2020 or 1/13/2020) | * Writing review (preliminary)
2020-02-03 | *Writing review & Evidence check |  |  | * Coordination with the writing team
|  | 2/4/2020 - 2/16/2020 | * Writing teams check progress on narrative development & evidence collection & alignment
2020-02-17 | * Writing review & Evidence check |  |  | * Coordination with the writing team
2020-03-16 | *Writing review & Evidence check |  |  | * Coordination with the writing team
(*Feedback from the college)
2020-03-30 | *Writing review & Evidence check |  |  | * Coordination with the writing team
2020-04-20 | * Writing & Evidence done at 75% point of completion |  |  | * Coordination with the writing team
2020-05-04 | * Writing & Evidence done at 80% point of completion | (Share draft with the college) |  | * Coordination with the writing team
(5/18/19) | * Additional time for catch up
Summer 2020 | * Edit narrative, align evidence
Fall 2020 | * College participatory overnance review * Board = first read, November * Board = second read, December * Early January 2021 = submission to ACCJC