## Sheet1
BCC 2021 ACCJC Institutional Self-Evaluation Report Preparation Plan (DRAFT)
Summer 2019 | Fall 2019 | Spring 2020 | Summer 2020 | Fall 2020 | Winter, January 2021 | Spring 2021
1. Late 6, early 7, connect with Dr. Stephanie Droker/ACCJC: * Eligibility requiremnent and current PCCD fiscal challenges * Timing of eligibility requirement submission * Substantive change submission dates (prioir to 9, 2020) based on prior submission by BCC and Sub. Change Committee's review dates. * Exact date of ISER submission in 1, 2021 (1-22-21?) | 1. Early 9, Role out of BCC ACCJC ISER preparation plan to the college community: * Call out for Faculty ALO (0.4FTE) and Faculty or Staff lead for each standard and identification of the evidence team, and an editor. (complete by 9/27) * Plan for the training of the team and community at large * Inform them that the Survey is coming their way * Meet with ACCJC late September. | 1. Surveys in early spring 2020: 2-18-20 or so. CCSSE - CC survey of Student Enggement (2013, 2015, 2017) and GP | Reserved for technical revisions. 1. Each team lead and editor polishes and clean up reports. Create consistency across the report. | 1. At the beginning of fall 2020, BCC ISER draft should be at 80% completion point with accompanied evidence. * Take drafts to BCC participatory governance groups for review and feedback. | 1. Final clean up of the ISER, Evidence check, and final wrap up of the ISER, be ready for subnission by mid 1, 2019 if not sooner. | 1. BCC ISER submission to ACCJC no later than by Friday, 1-22-21 (8weeks before the visit during 3-15-21 week), confirm with Dr. Sroker/ACCJC now.
2. Complete a draft of timeline andpreparation activities - Mid 7 * Idenfity BCC Accreditation preparation structure including a faculty ALO. * Identify Budget needs | 2. Week of 9/9 or 9/16, conduct First-Time Student Survey (Gap analysis) | 2. Each standard group begins writing their section based on the bullet points to the standard including the identification of evidence. * Provide template for writing each section and how evidence should be identified to each team. * Survey results should be used to write each section where appropriate. * Writing timeline will be provided to each standard group. * Editor edits as each writing team submits | 2. Evidence Team works on missing evidence, linking of the evidence to the section, and ensures that all links work. | 2. Be ready to take the Final Draft t BOT in 11 and 12, 2020 (confirm dates at the beginning of the semester)
3. Obtain a couple of Qualit ISERs from other institutioms. | 3. SLO/A & PR APU begins per the timeline (completion aimed at 11, 2019) | 3. Evidence team meets and ensures that each section of evidence is linked appropriately. | 3. Cross-reference content and standard requirements.
4. Assessment of Evidence: * Shared governanc agendas & minutes since 2017 *What's missing? * Who will be in charge of obtaining missing information? | 4. Mid-late 10, conduct BCC Accreditation survey per the standard and: * SLO/PLO/ILO * Participatory Governance * Campus Cliamate * Standard 3 & 4, District * Interest for Quality Essay topics Results to be summarized by late 11 or early 12, 2019. | 4. By late 4, 2020, Draft of the BCC ISER and its evidence should be at 65% completion point.
5. Brainstorm potential ideas for "Quality Essay" for BCC * Must be related to Student Learning & student Achievement | 5. Each standard group starts working on developing bullet points of each standard, complete by late 11, 2019. * Gap analysis: before writing them, what information is missing? Identify them by the end of fall 2019 semester. | 5. Coordination of information wiht the district's office particularly on standard 3 and 4.
6. Prepare for an initial "gap analysis" per the standard on a higher level. | 6. Regularly scheduled BCC ISER Steering committee meeting and writing team meeting will be taking place througout the fall 2019 semester.
7. Identify District Office (DO) ALO and define working relationship with the colleges. * Annette Danbrogio | 7. Coordination with the Districts with standard 3 and 4