# Instructional, Student Support, and Administrative Services

BCC Annual Program Update (APU) 2025-26 Timeline

| Dates | Activities | Leads | Notes |
| --- | --- | --- | --- |
| Mid- August | APU 25-26 Draft Timeline, expectations, guiding principles, and recommended process to be ready to be shared with the Shared Governance committees. | Cabinet, Researcher |  |
| 9/11/25 | IPC review of 25-26 APU draft timeline and template. Identify a Taskforce to finalize the template by 9/26/24. Assessment Committee provides their recommendation of the prompts and data for the COR section. | IPC members Assessment committee |  |
| 9/11/25 | IPC identified a small task force to finalize the tool by 9/26. Disaggregated data per department will also be ready by this time. | IPC Researcher | Reps from OOI, OSS, Admin Chris Susan Truong Phoumy Andrea Amy |
| Week of 9/29/25 | Tech committee Refresh plan to be shared with the Departments (so that the departments, programs, services will know what will be taken care of by the overall institutional perspective) |  |  |
| 10/7/25 | Budget Advisory Committee (BAC) review APU timeline and process APU tool and data be shared with the College community | BAC IPC |  |
| 10/8 to 11/26/25 | Deans/Supervisors work with each Department, program, and service leads during this time to complete the APU. Deans/Supervisors review, provide feedback to writers, and validate completion of APU. |  |  |
| 11-21-25 | Department Chairs and Academic Senate complete the faculty prioritization process for 2025-26. Present to Academic Senate on Dec 3, 2026. |  |  |
| 12/1- 12/12/25 | Researcher will compile resource requests for the Deans/Supervisors to review |  |  |
| 12/15- 1/16/26 | Deans/Supervisors, VPs, and President receive APUs to write division-level APUs and submit them to BAC |  |  |
| 1/19-1/23/26 | President & VPs submit prioritized resource requests to BAC |  |  |
| 1/27/26 | VPs & President units present prioritizing resources process for Fund 01, non-restricted funds, at BAC for endorsements |  | Jan XX BAC meeting |
| 2/2/26 | BAC makes recommendation for the Fund 01 to Roundtable Roundtable receives prioritized resources from BAC and if endorsed, makes recommendation to President. |  | Feb 2 or 9 Roundtable meeting |