## Sheet1
Timeline for the Berkeley City College Follow Up Report to the Accrediting Commission for Community and Junior Colleges Berkeley City College Community Addresses Recommendation #5 and Informs the District's Responses to Recommendations #2 Financial Audits, #3 Fiscal Stability and #4 Board Policy Due March 15, 2013
Benchmarks | Recommendation #5 Presentation to BCC Community | Share proposed Outline of BCC's Accreditation Response | Draft #1 of the Follow Up Report | Preliminary Draft of the Follow Up Report | Recommendations to College President | Draft to District Accreditation Team | Final Draft to Chancellor | Board Approval [Feb. 4 to R.Epstein for Board Agenda] | Submit to ACCJC
Due Dates | August 16 - September 30, 2012 | October 22-31, 2012 | November 15-30, 2012 | December 1-14, 2012 | December 14, 2012 | December 17, 2012 | January 31, 2013 | 1st reading: 2/12/13 2nd reading 2/26/13 | March 13, 2013
Activities | BCC's Professional Day activities highlighted BCC's planned response to Accreditation Follow Up Report due March 15, 2013 | Organize college forums and brown bag sessions to disseminate information on BCC's planned response to ACCJC recommendations. Share outline and ACCJC Institutional Planning Rubric. Demonstrate how BCC meets sustainability criteria. Discuss alignment with strategic planning & 2012-13 institutional goals. | Develop first draft of Report using input from college constituencies and program reviews. | Present Draft 1 to College Governance Committees and all Senates. Dec. 3: College Roundtable Dec. 5: Faculty Senate Dec. 6: Classified Senate Dec. 7: Department Chairs Dec. 12: Leadership Council ASBCC | Input from all sources is incorporated into draft, and document is forwarded to College President. | President's input is incorporated into document. | Provide final draft of Follow Up Report to Chancellor Ortiz | Feb 4: Present final Berkeley City College Follow Up Report to Chancellor's assistant, Ms. Roxanne Epstein, for submittal to the Board of Trustees | Submit Board approved Berkeley City College Follow-up Report to the ACCJC.
| Draft timeline and outline response to Recommendation #5; present to college governance committees. |  | Ensure that all programs, units, and college constituencies have opportunity to provide input by widely disseminating raw draft.
| Include response to Recommendation #5 as one of BCC's annual goals. | Advertise the forums and special brownbags college-wide. | Include sections on Fiscal and Administrative capacity. |  | President provides input. | Jan 28: Final draft shared with College Roundtable.
|  | Discuss ACCJC SLO Rubric with evidence of proficiency. | Highlight instructional and student services initiatives to support and enhance student success.
Responsible Parties | College President, ALO, Asst ALO, and members of the Leadership team | College President, ALO, Asst. ALO, VPSS, Fac Sen and Class Sen Presidents | ALO, Asst. ALO, PIO | ALO, Asst. ALO, Lead Editor | College President | ALO | College President | District Chancellor | College President/ ALO
| ALO, Asst. ALO, PIO | ALO, Asst. ALO, PIO | Lead Editor, ALO, Asst. ALO, PIO | ALO, Asst. ALO, Lead Editor | Lead Editor, ALO | Lead Editor, ALO, Asst. ALO | Lead Editor, ALO, College President | Lead Editor, ALO, College President | Lead Editor, ALO, College President
INTERESTED IN GETTING INVOLVED OR HAVE A QUESTION? Contact ALO Linda Berry (lberry@peralta.edu)