## Slide 1: BCC 2021 Accreditation Institutional Self-Evaluation Report (ISER)
ISER Preparation and Role of Participatory Governance Committees
College Roundtable for Budgeting and Planning
Kuni Hay, Vice President of Instruction
Institutional Accreditation Liaison Officer
10-14-19

## Slide 2: Outcomes
  Debrief: ACCJC Training, September 26, 2019
  Dr. Stephanie Droker, ACCJC
  What did we learn?
  What are some critically important factors for us to remember when preparing for the ISER?
  Preparation for ISER:
  Structure for the ISER development
  Preparation for ISER:
  Timeline and work flow
  Preparation for ISER:
  Detailed timeline and writing process, Fall 2019 and Spring 2020
  Resources
  6. Role of the Roundtable

## Slide 3: Debrief: ACCJC Training
What did you learn? Take away
What are some challenges?
Feedback and your needs?

## Slide 4: Structure for the ISER Development
College ALO: VPI Hay, Faculty ALO: Charlotte Lee
Standards | Standard I: Mission, Academic Quality and Institutional Effectiveness, and Integrity | Standard II: Student Learning Programs and Support Services Instructional Programs Library and Learning Support Services Student Support Services | Standard III: Resources Human Resources Physical Resources Technology Resources Financial Resources | Standard IV: Leadership and Governance Decision-Making Roles and Processes Chief Executive Officer Governing Board Multi-College District or Systems
Administrative Co-Lead(s) | Rowena Tomaneng Phoumy Sayavong | Stacey Shears Kuni Hay | Rowena Tomaneng Shirley Slaughter | Lisa Cook John Nguyen
Faculty/Classified Co-Leads | Sam Gillett | Susan Truong | Vincent Koo Barbara Des Rochers | Kelly Pernell Jennifer Lenahan
Standard Task Force Members |  |  |  | 
Participatory Governance Partners | *Integrated Planning Committee (PIC) *Roundtable | *Curriculum Committee * CE committee *Assessment Committee *Teaching & Learning Committee *Distance Education Committee *Student Services Council * Library *Learning Resources Center * Academic Senate | *Facility/Safety Committee *Technology committee * Distance Education Committee *Administrative Services | *Roundtable * Academic Senate *IPC *Classified Senate * Associate Student of Berkeley City College (ASBCC)

## Slide 5: Timeline and Workflow
(See handouts)
BCC 2021 ACCJC Institutional Self-Evaluation Report Preparation Plan (DRAFT) |  |  |  |  |  | 
Summer 2019 | Fall 2019 | Spring 2020 | Summer 2020 | Fall 2020 | Winter, January 2021 | Spring 2021
1. Late 6, early 7, connect with Dr. Stephanie Droker/ACCJC: * Eligibility requiremnent and current PCCD fiscal challenges * Timing of eligibility requirement submission * Substantive change submission dates (prioir to 9, 2020) based on prior submission by BCC and Sub. Change Committee's review dates. * Exact date of ISER submission in 1, 2021 (1-22-21?) | 1. Early 9, Role out of BCC ACCJC ISER preparation plan to the college community: * Call out for Faculty ALO (0.4FTE) and Faculty or Staff lead for each standard and identification of the evidence team, and an editor. (complete by 9/27) * Plan for the training of the team and community at large (9/26/19) * Inform them that the Survey is coming their way * Meet with ACCJC late September. | 1. Surveys in early spring 2020: 2-18-20 or so. CCSSE - CC survey of Student Enggement (2013, 2015, 2017) and GP | Reserved for technical revisions. 1. Each team lead and editor polishes and clean up reports. Create consistency across the report. | 1. At the beginning of fall 2020, BCC ISER draft should be at 80% completion point with accompanied evidence. * Take drafts to BCC participatory governance groups for review and feedback. | 1. Final clean up of the ISER, Evidence check, and final wrap up of the ISER, be ready for subnission by mid 1, 2019 if not sooner. | 1. BCC ISER submission to ACCJC no later than by Friday, 1-22-21 (8weeks before the visit during 3-15-21 week), confirm with Dr. Sroker/ACCJC now.
2. Complete a draft of timeline andpreparation activities - Mid 7 * Idenfity BCC Accreditation preparation structure including a faculty ALO. * Identify Budget needs | 2. Week of 9/23, sent out the First-Time Student Survey (Gap analysis), closes on 10/11. Survey results to be compiled by 10/25. | 2. Each standard group begins writing their section based on the bullet points to the standard including the identification of evidence. * Provide template for writing each section and how evidence should be identified to each team. * Survey results should be used to write each section where appropriate. * Writing timeline will be provided to each standard group. * Editor edits as each writing team submits | 2. Evidence Team works on missing evidence, linking of the evidence to the section, and ensures that all links work. | 2. Be ready to take the Final Draft t BOT in 11 and 12, 2020 (confirm dates at the beginning of the semester) |  | 
3. Obtain a couple of Quality ISERs from other institutioms. | 3. SLO/A & PR APU begins per the timeline (completion aimed at 11, 2019) | 3. Evidence team meets and ensures that each section of evidence is linked appropriately. | 3. Cross-reference content and standard requirements. |  |  | 
4. Assessment of Evidence: * Shared governanc agendas & minutes since 2017 *What's missing? * Who will be in charge of obtaining missing information? | 4. Mid-late 10, conduct BCC Accreditation survey per the standard and conduct gap analysis: * SLO/PLO/ILO * Participatory Governance * Campus Cliamate * Standard 3 & 4, District * Interest for Quality Essay topics Results to be summarized by late 11 or early 12, 2019. | 4. By late 4, 2020, Draft of the BCC ISER and its evidence should be at 75% completion point. |  |  |  | 
5. Brainstorm potential ideas for "Quality Essay" for BCC * Must be related to Student Learning & student Achievement | 5. Each standard group starts working on developing bullet points of each standard, complete by late 11, 2019. * Gap analysis: before writing them, what information is missing? Identify them by the end of fall 2019 semester. | 5. Coordination of information wiht the district's office particularly on standard 3 and 4. |  |  |  | 
6. Prepare for an initial "gap analysis" per the standard on a higher level. | 6. Regularly scheduled BCC ISER Steering committee meeting and writing team meeting will be taking place througout the fall 2019 semester. |  |  |  |  | 
7. Identify District Office (DO) ALO and define working relationship with the colleges. * Annette Danbrogio | 7. Coordination with the Districts with standard 3 and 4 |  |  |  |  | 

## Slide 6: Timeline and Workflow
ISER development period:
Fall 2019 and Spring 2020
Spring 2020: college-wide review and feedback - twice
80% completed by May 2020
Summer 2020: Editing, Evidence validation, alignment, and
other technical revision and clean up
Fall 2020: BCC Participatory governance review
November 2020: First review by the Board
December 2020: Second Review & approval by the Board
January 2021: Submission of BCC ISER to ACCJC
Mid March 2021: Team visit

## Slide 7: Writing: Detailed timeline and process
Steering Committee meetings | Steering Committee focus | Writing Team Timeline or meetings | Writing Team activities and focus | Evidence Tream
 |  | 4-Oct | * Confirm Faculty ALO * Confirm Faculty or Classified Co-leads per the standard | * Team set up * Review ACCJC format * Identify depository * Ask participatory governance to start organizing agendas and minutes from 3 years ago.
10/7/2019 | *Introduction of the Steering Team *Writing team set up process * Review of the writing process (Draft Development) * Review Guide to Institutional Self-Evaluation, Improvement, and Peer Review (Possible Source of Evidence and Review Criteria) * Review Timeline |  |  | 
 |  | 10/17/2019 | * Writing members of each Standard to be confirmed by the Co-Chairs | 
10/21/2019 | * Share writing team members (co-leads) * Review overall process: format for responses to the questions. * Begin bullet points of outline per question. * Evidence collecion begins per Standard |  |  | * Coordination with the writing team
 |  | 10/21 - 11/4 (2 weeks) | * Each writing team designate members to wrok on questions within the standard * Begin producing outlines | 
11/4/2019 | * Check on progress on the outlines & evidence |  |  | * Coordination with the writing team
 |  | 11/5 - 11/18 (2 weeks) | * Bullet points productin & evidence collection continues | 
11/18/2019 | * Chek on progress o the outlines & evidence |  |  | * Coordination with the writing team
 |  | 11/19 - 12/1 (2 weeks) | * Be ready to complete bullet points/outlines by 12/2/19 | 
12/2/2019 | *Outline completed, be ready to write narrative *Discuss Narrative writing based on the bullet points, set timeline for writing process for spring 2020 *Member assignments for writing narrative completed. |  |  | * Coordination with the writing team
(12/16/2019) | * Additional time to regroup as necessary to be ready for writing |  |  | 
(1/6/2020 or 1/13/2020) | * Writing review (preliminary) |  |  | 
2/3/2020 | *Writing review & Evidence check |  |  | * Coordination with the writing team
 |  | 2/4/2020 - 2/16/2020 | * Writing teams check progress on narrative development & evidence collection & alignment | 
2/17/2020 | * Writing review & Evidence check |  |  | * Coordination with the writing team
3/16/2020 | *Writing review & Evidence check |  |  | * Coordination with the writing team
 |  | (*Feedback from the college) |  | 
3/30/2020 | *Writing review & Evidence check |  |  | * Coordination with the writing team
4/20/2020 | * Writing & Evidence done at 75% point of completion |  |  | * Coordination with the writing team
5/4/2020 | * Writing & Evidence done at 80% point of completion | (Share draft with the college) |  | * Coordination with the writing team
(5/18/19) | * Additional time for catch up |  |  | 
Summer 2020 | * Edit narrative, align evidence |  |  | 
Fall 2020 | * College participatory overnance review * Board = first read, November * Board = second read, December * Early January 2021 = submission to ACCJC |  |  | 

## Slide 8: Writing: Detailed timeline and process
BCC ISER Steering Committee:
AO, Faculty ALO, Co-Leads of each Standard
Twice/month, opposite date/time from Roundtable (on BCC Participatory governance calendar)
Fall 2019:
Bullet point per statement/question
Evidence collection and organization
Spring 2020:
Writing per ACCJC format, By May 4, 2020

## Slide 9: ISER format per ACCJC
Instructional Programs
All instructional programs, regardless of location or means of delivery, including distance education and correspondence education, are offered in fields of study consistent with the institution’s mission, are appropriate to higher education, and culminate in student attainment of identified student learning outcomes, and achievement of degrees, certificates, employment, or transfer to other higher education programs. (ER 9 and ER 11)
POSSIBLE SOURCES OF EVIDENCE*:
The college catalog—program descriptions show that programs align to the mission, are appropriate to higher education, and culminate in student attainment of learning outcomes and achievement of degrees, certificates, employment, and/or transfer;
Program brochures and web pages that describe the same;
And/or other documents that demonstrate the institution is aligned with this Standard
(Data on student degree/certificate completion, transfer, and job placement are already included in the ISER section on Student Achievement and do not need to be repeated here as evidence that programs culminate in achievement of degrees, etc.)
REVIEW CRITERIA:
All course and program offerings, whether traditional or distance education and/or correspondence education (DE/CE), align with the stated mission of the institution.
        Course and program offerings are appropriate for post-secondary education.
        Program descriptions include expected student learning outcomes and list the degrees and certificates that can be earned.
        The institution can supply data that students actually achieve degrees and

## Slide 10: Resources
PP from September 26, 2019 training
ACCJC Guide to Institutional Self-Evaluation, Improvement, and Peer Review
https://accjc.org/publications/
3. Checklist for the Steering Committee Co-Chairs