## Sheet1
| July | August | September | October | November | December | January | February | March | April | May | June | Notes
Schedule development |  | August 1 - final Spring submit to Deans | Sept 15- Spring back to Chairs for corrections | October 1 - Corrections Due to Deans, Prep for Print Mid -October - District Download Spring and goes to print Last week of Oct. - Print out | 2nd week of Nov. - Registration for Spring begins 2nd week of Nov. Start building Su/Fall - roll over schedules to Chairs | 2nd week of Dec. Su due to Deans | Jan. 15- Fall Due - to Deans, Su back to chairs for corrections | 2nd week Feb - su back to Deans, Fall back to chairs for corrections Last week of Feb - Fall corrections back to Dean | Mid -March - District Download Su/Fall and goes to print Last week of March - Print out | 2nd week of April - Registration for Su/Fall 2nd week of April Start building Sp - roll over schedules to Chairs |  |  | **dependent on when students get to registe. Should have public at least two weeks before registration starts
Curriculum | Proposals in queue | dept review/approvals | tech review/approvals | tech review/approvals | finalize approvals | articulation deadlines | identify curriculum updates due upcoming year and new curriculum needs | discuss new curriculum needs | discuss new curriculum needs | faculty to develop new curriculum | faculty to develop new curriculum | Proposals in queue
Outcomes Assessment |  | discuss data gathered from previous term include into PR/APU | conduct assessment | conduct assessment | enter data | compile data | discuss data gatheredfrom previous term and include into PR/APU | conduct assessment | conduct assessment | enter data | compile data
Faculty Evaluations | develop list to evaluate | provide lists to chairs to identify evaluators | conduct evaluations | conduct evaluations | dicuss with faculty | complete paperwork and turn in | provide lists to chairs to identify evaluators | conduct evaluations | conduct evaluations | dicuss with faculty | complete paperwork and turn in
Program Review/APU | July: Beginning of July - Post Data on Access. Equity and Success Mid to End of July - Admin plan for Beginning of year planning work; August: First week of August -Chairs/Deans/VP meet to discuss Flex Day Plans At College Flex Day - President to present data from previous year and long-term goals. VP/Dean presents at dept cluster meeting - data for the clusters/dept in alignment with College goals Chairs lead discussion and work on reflection and plan's the coming year's work. 1st Chairs meeting -- chairs present department goals.; September: At First Roundtable - Deans to present the Dept. Clusters goals aligned with College goals Dept Cluster/Dept meetings - to determine actions to meet goals and identify needs; October: October 1 - Program Review/APU due to Deans with rec for Curriculum, Supplies & Equip, Tech, Facilities, HR, and Prof.Dev. 1st week in October - Chairs to present PR/APU's as info item to gather feedback. 3rd week in Oct. - Senates to provide rec. for action re: PR/APU at Roundtable.; November: 1st Nov. Roundtable -Dean's present summary's and prioritized needs. Mid-Nov - Roundtable recommends actions on; June: Gather end of year data on Access, Equity and Success | Program review should address learning outcomes for students in the program and address access, equity and success goals for all students in the program. Enrollment management should identify ftef ,ftes goals, trends, etc.
Budget | Load budget | Disburse to dept clusters/dept. | Final budget approved for the year by board. | BSI Report due |  | compile budget requests and recommendations from PR/APU | Spring Flex day - President to present budget priorities based on Ed. Master Plan and PR/APU.End of month - Budget director to present next year's budget proposal after Gov. puts out budget info | Ed committee to propose funding priorities based on Ed Master plan goals and PR /APU's 2nd meeting of month Funding considerations for next year presented to campus | 1st week of March Senates provide recommendations of funding 2nd meeting of month Rountable to discuss funding proposals | 1st meeting Roundtable to recommend funding to pres Mid April - Pres to finalize funding for next year Perkins budget report turned in | May Revise | Tentative budget presented to board. | monthly monitoring to determine if expenses are on target.
Faculty/Staff Prioritization | Gather data to determine where we are with Ed Master Plan goals | Present to campus update on the Ed Master Plan for use in PR/APU | Identify Faculty/Staff needs per the Ed Master Plan | Present priority areasof need to campus. Determine alignment with PR/APUs through presentations | 1st meeting Present proposed priority list for vetting 2nd meeting Recommend to Roundtable | 1st meeting Recommend to Pres Before break President decides | Spring Flex - Pres to present hiring plans | Hiring announcements | Hiring Interviews | Hiring Interviews | Hiring Decisions made and forwarded to Board | Hiring Intake for Fall